## Sprint 1
Project Name-Home Loans |  |  |  |  | TEAM MEMBERS: Priyanshi Soni -10683821 Suhani Garg -10684223 Sagar Sidhwa -10684142
User Story | TO DO | In Progress | Impediment | To Verify | Done
A Home page which provides an overview about our organization and allows new users to register. Allows users to register themselves in our online portal and registered users to login. | 1.1 Create EMI and Eligibility Calculators-[Suhani Garg] 1.2 Popup functionality on HomePage for admin and User redirection and Alert messages-[Suhani Garg] 1.3 Creating Admin And User Login Functionality-[Priyanshi Soni] |  |  |  | All the requirements of this user story have been completed.
2. Creating The Application for users to apply for loan | 2.1 Develop Tables in Database corresponding to each application form requirement-[Sagar Sidhwa,Suhani Garg,Priyanshi Soni] 2.2 Develop Web API controllers and Model classes corresponding to each table-[Sagar Sidhwa,Suhani Garg,Priyanshi Soni] 2.3 Creating user's Personal Details form(Frontened and Backend)-[Priyanshi Soni] 2.4 Creating Income Details(Frontened and Backend)-[Priyanshi Soni] 2.5 Creating Property Details Form(Frontend and Backend)-[Suhani Garg] 2.6 Creating Loan Details Form(Frontend and Backend)-[Suhani Garg] 2.7 Creating Documents form and devloping controller for document upload(Frontend and Backend)-[Sagar Sidhwa] 2.8 Creating User's Dashboard showing all the application details from previous forms and generated application number-[Sagar Sidhwa] 2.9 Creating Loan Tracker that takes apllication no. & mobile no. and tells application status and Account tracker to check account balance once application is approved and account no. is generated -[Sagar Sidhwa] |  |  |  | All the requirements of this user story have been completed.
3.Creating Admin's Interface | 3.1 Creating Register Admin Form(Frontend and Backend)-[Priyanshi Soni] 3.2 Creating the Admin view Dashboard where he can see all the applications assigned to him for verification, View all Details in that application and devloping a logic where admin can change the status of the application to approved or rejected-[Sagar Sidhwa] |  |  |  | All the requirements of this user story have been completed.
4. Add Beneficiary, Change Password, Forget Password,FAQs,About Us,Features. | 4.1 Change Password components for users and admins-[Priyanshi Soni] 4.2 FAQ's-[Priyanshi Soni] 4.3 About Us and Features-[Priyanshi Soni] | Forgot Pasword |  |  | Change password components,FAQ's,About Us and Features.

## Sprint 2
User Story | TO DO | In Progress | Impediment | To Verify | Done